## Slide 1: Building, Implementing & Troubleshooting an Automatic Referral for Cardiac Rehabilitation
Notes:   This presentation is designed to help you understand the steps required for designing, testing, implementing, and troubleshooting an AR system in your hospital/health system.
  IMPORTANT NOTE RE: ACCESSING LINKS in this PPT presentation:
  Links embedded in SLIDE portion are hyperlinks
  Links shown in the NOTES portion must be copied into a browser to be accessed

## Slide 2: Acronym List

## Slide 3: Overview of TAKEheart Materials for Implementing AR
Consolidated Curriculum for Implementing AR
  PPT Slides
  Implementation Guide (IG)
  Resource Guide (RG)
Original Training Modules
  #5: Building and Implementing a Successful Automatic Referral System
  #7: Troubleshooting Your Automatic Referral System
Other Related Webinars
  Cerner Q&A
  Epic Q&A
(Please read notes below to learn more about these materials)
Notes: There are three components to the Consolidated Curriculum for Implementing AR that are designed to be used together:
1. This slide deck:
The slides are focused on broadly describing the recommended activities (“WHAT”) and explaining “WHY” they are being recommended.
The information is presented in a PPT format so that it can easily shared with other staff whose support or involvement may be needed during implementation.
Notes are included for some of the slides -- where the slide is not self-explanatory, or to include additional content
2. IG: This PPT presentation is meant to be used alongside the Implementing AR Implementation Guide (IG).
The IG provides actionable, step-by-step guidance about HOW to implement the actions recommended in the slides.
If you are just beginning to plan your QI initiative, you may want to start by reviewing the slide deck alone.
Once you are ready to launch and implement, you may find it helpful to use these two sets of materials side by side, one section (‘step”) at a time. (The same section titles (STEPS) are used in the PPTs and IG).
Chapter titles in slides align with chapter titles in the IG
3. RESOURCE GUIDE: Those wishing to dig even more deeply are encouraged to review the companion Implementing AR RESOURCE GUIDE
This Guide includes additional information and guidance -- in the form of tools, templates. articles, case studies, videos, slide decks, and more -- for anyone wishing to dig even more deeply into the core topics covered in this presentation.
ORIGINAL TRAINING MODULES: The original training modules are one hour-long training sessions originally presented live to a group of hospitals working in real time in 2020-2021 to implement AR. The Consolidated Curriculum for Implementing AR is a streamlined, restructured synthesis of the information presented during these original trainings. (Links to these sessions and brief descriptions of their contents - are also included in the “ To Learn More” slides in this slide deck for those wishing to hear directly from experts and peers about their own experiences with implementing AR in their hospitals or health systems.
The TAKEheart WEBINARS, hyperlinked from this slide, are one-hours sessions held between 2020–2022, featuring discussions among CR experts and CR champions from diverse hospitals.
The Cerner and EPIC Q and A webinar were led by a teams of Cerner and EPIC experts respectively, and provide answers to common implementation issues from both the clinical and IT perspectives.
.

## Slide 4: Overview of Implementation Process
Lay Groundwork for QI
Plan
Design
Test
Train Staff
Rollout & Reinforce
Evaluate & Improve
Extend & Spread
Notes:   The flow chart above provides an overview of the entire process described in the TAKEheart materials for Implementing AR.
  The first box -- laying the groundwork for QI – is the subject of the entire Getting Started Curriculum.
  We will briefly review the key steps for laying the groundwork for QI in the next set of slides
  However, recommend beginning with the Getting Started Curriculum, especially if you have not implemented a QI initiative in the past.
  NOTE: If you recently reviewed the Getting Started materials, you may wish to go skip the review and go directly to Chapter 1

## Slide 5: Be Advised: Implementing AR Takes Time!
Successfully implementing AR is NOT a simple reprogramming of an EMR!
Even hospitals with well-operating EMRs and strong IT support may need several months to get their AR systems up and running.
Notes: There will be wide variation across hospitals in the length of time needed to work through the steps described here. Since successfully implementing AR is NOT a simple reprogramming of an EMR, for most hospitals the process is likely to take several months

## Slide 6: Table of Contents
Look Back: Review of Key Foundational Steps
Chapter 1: Understanding Automatic Referral
Chapter 2: Defining Eligibility
Chapter 3: Creating EMR Specifications
Chapter 4: Testing and Fine Tuning
Chapter 5: Preparing to “Go Live”
Chapter 6:Data and Feedback Monitoring
Chapter 7: Post-Launch Troubleshooting
Notes:   The titles above are hyperlinks, to enable you to skip ahead to any Chapter in the presentation. You can also return to the table of contents using the hyperlink embedded in title slide for each section.
  The Chapter titles in this PPT presentation match the titles used in the Implementation Guide.

## Slide 7: Review of Key Foundational Steps

## Slide 8: Critical First Steps for QI for CR
Recruit a strong cardiac rehabilitation (CR) champion
Assemble a multidisciplinary team
Create an aim statement
Develop an action plan
Map and study current workflow processes to develop a deep understanding of the current state before redesigning
Explore data collection and decide data needed to support implementation of automatic referral (AR)
Notes:   Every QI project starts by creating a strong foundation. YOU WILL NOT SUCCEED IN IMPLEMENTING AR if you have not done so.

## Slide 9: Engage Key People
Patients
Cardiac Rehabilitation Champion
Quality Improvement Specialist
Reporting and IT Analytics Coordinator
Ordering Provider
IT Dept. Representatives
Notes:   Getting the perspectives and insights of the people who will be impacted by your intervention is essential. For example, if the physician assistants and/or residents write the orders, have conversations with them. Speaking only with attendings will likely result in critical mis-steps that decrease the efficacy of your program and increase end-user frustration.
  An important way to engage key people is by involving them in a workflow mapping process, described in the Getting Started materials. MAPPING WORKFLOW PROCESSES before starting the process of implementing AR will be critical for its success!
  You will also want to measure performance rather than assuming success. So, it is crucial to have someone analyze the data to check improvement or identify unusual patterns that need investigation.
  Both IT and clinical staff share important roles in the design of your AR process. Your CR champion plays a particularly critical role in this project. Referring to external programs, for example, might be a sticking point for some institutional leaders. The skills of your CR champion can be useful in navigating these kinds of issues. (If you are trying to improve referrals to an external systems and programs, consider including the insights of representatives of those programs on the referral process.)

## Slide 10: Define a Clear and Compelling Aim
Include a S.M.A.R.T.* goal in your aim.
Example
We aim to increase the number of qualifying patients with MI, PCI, and CABG who participate in at least 1 CR session by 30% by December 31, 2022. A key process goal is to implement automatic referral with care coordination by March 31, 2022.
* S.M.A.R.T. = Specific, Measurable, Applicable, Realistic, & Timely
Notes:   Create an aim statement to serve as the compass for the project. One of the major tasks is to create an order mechanism that fits seamlessly into workflow processes which identifies and drives more patients to CR, any CR. Because patients come to the hospital from many communities, many hospitals refer to both their own and external CR programs depending on what is most convenient for the patient. It is important to know the availability of CR locally, as well as in the outlying areas.

## Slide 11: Keys To Success
Strong executive sponsorship and support with a shared understanding of project importance
Clear project ownership
Clear governance and decision making
Strong project management
Collaboration with key stakeholders, including end users (front-line staff, patients)
Notes:   This slide and the next list keys to success. Commitment from hospital and departmental leadership and a strong champion are at the top of the list. The project also needs to have a clear owner supported by strong project management with clear lines of decision making.
  Since IT departments have long lists of projects waiting, your CR champion may have to negotiate to raise automatic referral up the list and will likely need leadership support to do so. However, you can’t just hand the project over to IT. IT projects that are done in isolation without clinical input are never as successful as those that are done in a collaborative fashion with clinical subject matter experts.

## Slide 12: Keys To Success: Action Plan
Clear, achievable goals
Adequate resources and budget
Well-defined tasks with clear responsibilities
Realistic timelines for completing tasks
Proper mix of skills among teams
Notes: Another key to success is a clear and realistic Action Plan as described on this slide. Guidance and tools to help you create an action plan are included in the Getting Started IG. https://www.ahrq.gov/sites/default/files/wysiwyg/takeheart/training/getting-started-implementation-guide.pdf

## Slide 13: Common Causes of Failure
Unclear project requirements
Poor management
Lack of communication
No end-user involvement
Lack of quality testing
Notes:   Here is a list of the most common reasons projects fail. Take note of these and keep them in mind as you plan and implement AR for your institution. Your action plan is one of the most important tools you can use to avoid the pitfall of poor project management. You can prevent some of the main reasons that projects like AR implementation fail by:
  Ensuring that tasks are clearly assigned and that there’s agreement on when they will be completed
  Tracking and reviewing progress with your team

## Slide 14: Chapter 1: Understanding Automatic Referral
Notes:   The next set of slides will work to establish a common understanding of AR.

## Slide 15: What is Automatic Referral?
Automatic electronic medical record-based CR referral
Referral built into an order set
Default, “opt-out” model
All patients with a qualifying diagnosis and/or procedure are referred
All relevant providers are notified
Notes:   The TAKEheart definition of AR is rooted in the scientific evidence established by Dr. Sherry Grace and her research team and reinforced by the Million Hearts initiative. AR is an electronic medical record-based CR referral built into an order set in such a way that all patients with a qualifying diagnosis are referred by default unless the physician takes action to remove the order.
  Automatic referral is NOT a pop-up message that emerges in the patient’s medical record giving the clinical provider a choice about referring the patient to CR.

## Slide 16: Referral Patterns
Internal CR Program
Eligible patients in your hospital
Eligible patients in other hospitals / practices using your EMR
Eligible patients in other hospitals / practices with an EMR that can interface
Eligible patients in other hospitals / practices with an EMR that can’t interface
External CR Program
Notes:   Patients take many paths to reach outpatient CR. While referrals from all these environments are important, TAKEheart is focused on the design and implementation of automatic referral from the inpatient/procedural environment to outpatient CR. We recognize that some of you may be looking to automate referrals from other environments. The EMR system will be a major driver since there must be way for the referral to be communicated from one environment to the other.

## Slide 17: Ease of Implementation
Easiest | Eligible patients + Your Site + Your EMR | This is the focus of TAKEheart and the best place to begin. It easily allows for working on both AR and care coordination processes.
 | Eligible patients + Other Sites + Your EMR | IT changes are likely the same as above. More work will be required to gain provider buy-in and more people will need to be involved.
 | Eligible patients + Other Sites + EMR that can interface | Requires embedding automatic referral in two separate EMRs and more people need to be involved in care coordination planning.
 | Eligible patients + Other Sites + EMR that can’t interface | AR can’t be implemented without two interfacing EMRs. Strengthening care coordination is an alternative.
Hardest | External Programs | Automatic referrals outside the system may not be a financial priority. Strengthening informal referral processes is an alternative.
Notes:   The focus of TAKEheart is the implementation of AR in a hospital/procedural setting for that site’s eligible patients using that site’s EMR. Including other sites and other EMR systems increases the difficulty of implementation.

## Slide 18: What Constitutes a Completed Referral?
A Good Start
AR
Better
Required for hospitals to get referral credit
  AR
  Patient Conversation
Best
AR
Patient Conversation
CC/First CR Scheduled
AR = AR of eligible patient to CR with guidance in discharge papers
Patient Conversation = Ordering clinician conversation with patient to endorse/recommend CR
First CR Scheduled = Patient’s first CR visit is scheduled prior to discharge
Notes:   Automatic referral is good, but, for the sake of your patients, we want to empower you to do your best. For hospitals to meet accreditation requirements and get credit for a referral, a conversation must take place between the ordering physician and the patient. This conversation also significantly increases the likelihood that the patient will actually enroll in CR. The best definition of a completed referral is when an eligible patient is referred, a conversation takes place, AND the patient is scheduled for their first visit prior to discharge. This of course further increases the likelihood that the patient will participate in CR.

## Slide 19: Automatic Referral Makes Care Coordination MORE Important
AR is not a substitute for the “Human touch”
More referrals should lead to more conversations with patients and families about CR
Cardiologist recommendations and family support strongly impact CR participation
Notes:   As mentioned on the prior slide, it is important to point out that automating referral is not a substitute for a clinician conversation with the patient about cardiac rehabilitation. The human interaction and conversation with the patient and family about CR is a strong influencer of patient participation in CR. The AR and the healthcare provider conversation with the patient and family work in concert.

## Slide 20: Automatic Referral Addresses Problematic Beliefs
Problematic Beliefs | AR Solution
“CR will not be beneficial” | Referrals made using consistent, evidence-based criteria
“The patient will not attend, so why bother?” | Implicit biases excluded from automated referral
Notes:   There are some who believe CR is not beneficial. AR promotes consistent referral of eligible patients based on evidenced-based criteria. AR excludes implicit biases held by some providers.

## Slide 21: Automatic Referral Addresses Process Failures
Problem Processes | AR Solution
Uncertainty about who is responsible for making the referral or if someone has already referred the patient | EMR makes the referral and appropriate physician retains ability to opt-out the patient
Uncertainty about whether the patient meets inclusion and/or exclusion criteria | EMR programmed to consistently identify eligible patients
Uncertainty about when, the patient can begin CR or how the referral should be made | Referral consistently embedded into discharge order set
Notes:   AR allows for consistent timing and execution of the referral. Sometimes there is uncertainty about when the patient can begin CR: (in the hospital, after procedure, or following hospitalization). There can also be uncertainty about processes related to informing the patient about CR: tell the patient, enter CR into the discharge order set, notify the CR program, or a combination of approaches. Occasionally, confusion develops about who is making the referral. AR removes the guess work about who is making the referral at the same time the physician retains the ability to opt the patient out. The last process failure is uncertainty about the eligibility requirements for CR. Programming eligibility criteria into the EMR leads to consistent identification of eligible patients, taking the guess work out of deciding who qualifies and who doesn’t.

## Slide 22: To Learn More …
See Chapter 1 of the AR Implementation Guide for:
A definition of AR
Types of referral patterns
What constitutes a completed referral
Putting together an AR Implementation Team
Roles and responsibilities for AR Implementation Team members
An overview of common errors in EMR Implementation

## Slide 23: Chapter 2: Defining Patient Eligibility
Notes:   The next few slides provide a general overview of the eligibility criteria for CR.

## Slide 24: Eligibility Discussions
Successful AR depends on decisions made ahead of time about which patients are appropriate and eligible and which are inappropriate for CR.
Stakeholders must discuss and reach consensus and buy-in around defining eligibility criteria for CR.
Notes:   Discussions need to take place to reach consensus on which patients are eligible and which are inappropriate.

## Slide 25: Eligibility Criteria
Heart attack in the last 12 months
Coronary artery bypass surgery
Current stable angina
A heart valve repair or replacement
A coronary angioplasty or coronary stent
A heart or heart-lung transplant
Stable chronic heart failure
Notes: Here is a list of the general eligibility criteria. More detailed information – including a table of ICD and CPT codes -- can be found in the on pages 4-7 of the Implementation Guide. https://www.ahrq.gov/sites/default/files/wysiwyg/takeheart/training/implementing-automatic-referral-implementation-guide.pdf

## Slide 26: WHO: Include Eligible Patients
PROCEDURE
(CPT codes)
  Cath Lab procedures
      PCI
  Surgical procedures
      CABG
      Heart valve replacement/repair
      Heart or heart/lung transplant
DIAGNOSIS
(ICD-10 codes)
  MI
  Chronic stable angina
  Chronic stable heart failure
      Ejection fraction=<35%
      Outpatient referral
      Medicare guidelines: 6 weeks post hospital
Notes:   The specific codes associated with the procedures and diagnoses shown on this slide are presented in the MH Outpatient CR Use Surveillance Methodology: https://millionhearts.hhs.gov/files/Cardiac-Rehab-Use-Surveillance-Guidance-508.pdf
  BE ADVISED:
  It’s likely that you’ll find the EMR doesn’t function the way you thought it did. No matter where you are in the automatic referral design process, sit down with your IT professionals and find out how the referral system currently identifies patients who should receive CR. This is especially important if you did not involve IT staff in the mapping process.
  One common problem is that electronic health record systems often store diagnosis codes in multiple places. The visit diagnosis often indicates the ICD-10 code for a clinical encounter. In a different location there may be a problem list contains all the ICD-10 codes associated with a patient. Often, the problem list is not up to date. For AR to work the way it should, you’ll need to work with your coding and documentation departments and do a walk-through of the EMR system to identify the best source for codes.
  Make sure that your IT professionals understand that you’ll need to use CPT codes for both interventional cardiology and surgical procedures so your AR system also captures those patients.

## Slide 27: WHO: Eliminate Inappropriate Patients
Exclude comorbidities and conditions for which CR would be contraindicated
Notes:   Being able to identify the “wrong” patients for CR is just as important as identifying the “right” ones. It is obvious, for example, that patients in hospice care would not be appropriate for CR referral. Likewise, patients with an existing referral don’t need another one. Consider a filter mechanism in the AR design. The team, using their collective perspectives, needs to create a list of diagnoses/procedures to include and comorbidities/conditions to be filtered out/excluded.
  Keep in mind that every time the system prompts a care provider to refer a patient to CR and thinks, “stupid system, this patient isn’t appropriate for cardiac rehab,” you risk that provider questioning or even ignoring the prompt in the future for patients who are appropriate for referral

## Slide 28: To Learn More…
See Chapter 2 of the AR Implementation Guide for:
Patient eligibility and exclusion criteria
Important discussions to have with respect to eligibility
A guide to having these discussions
CR Eligible ICD-10 and CPT codes

## Slide 29: Chapter 3: Creating EMR Specifications
Notes:   This chapter presents information about the design of the AR.

## Slide 30: Accounting for Order Sets
What are order sets?
A group of standard provider directives and or instructions regarding the care of a patient.
A clinical decision support tool prompting physicians to order appropriate treatments based on evidence-based practices.
Order sets for AR
Physicians use the order sets for AR to increase CR enrollment among eligible patients.
Notes:   To start the discussion of designing the AR system, we want to establish a common understanding of order sets.

## Slide 31: Four Crucial Design Factors
Who
When
How
Where
Notes:   Determining WHO is and isn’t eligible for CR is the first of four factors that must be addressed in designing successful automated referral system. This was discussed in the previous chapter.
  The other three factors are WHEN, HOW and WHERE

## Slide 32: WHEN: Best Times to Trigger Referral
Embed the referral mechanism into an actual “encounter of care” when the patient is in a receptive state there is an opportunity for conversation with the patient and family.
Notes:   Embedding the referral mechanism into an actual “encounter of care” provides the opportunity for a care provider to discuss it with the patient and family. Whether at discharge or during a care encounter, these are points in the care process the patient is receptive to receiving information and advice.
  Studies show including AR in the discharge order set is the best way to boost utilization. While this should be the goal, EMR systems vary. Some EMR systems are set up to identify patients at admission. Work closely with your IT team to understand your system’s abilities and limitations.

## Slide 33: HOW: AR from Inpatient Setting
Inpatient Setting:
Align your AR process with your existing workflow as much as possible
Insert AR into tools already being used, i.e., discharge order set
Include a way for physicians to cite their reason for clinician “opting-out”
Include a way for users to provide physician feedback to inform future refinements
Notes: For AR to function properly, it must be designed with particular EMR specifications in mind. This slide lists steps for approaching this part of the implementation process for an inpatient setting. Successful completion of the workflow mapping process, described in the Getting Started slides https://www.ahrq.gov/sites/default/files/wysiwyg/takeheart/training/getting-started-slides.pptx and Implementation Guide, https://www.ahrq.gov/sites/default/files/wysiwyg/takeheart/training/getting-started-slides.pptx is critical first step for ensuring that your AR process will align with existing workflows.
Here are a few additional tips:
  Gather information about the reasons providers are opting not to refer specific patients. Work with IT to build reason codes into the EMR system or survey a sample of physicians who override to uncover reasons. This data may help to inform future refinements of your AR.
  Use rules behind the scenes so that things get incorporated into tools that people already use…for example, if you have a discharge order set that’s used for all your patients, and if the patient has certain characteristics (e.g., MI or CABG), you can add in an additional section to that order set.

## Slide 34: HOW: AR from Outpatient Setting
Outpatient Setting:
Create a “hard-stop” alert
Program the alert to flag appropriate providers (e.g., cardiologists and internists not dermatologists) to make a selection during the care encounter
Require providers to select an action for all patients with qualifying diagnoses, e.g., heart failure, recent MI
Notes:   When AR is being implemented in an outpatient setting, we recommend creating a “hard stop” during the care encounter. A hard stop will require the provider to make a selection in order to move on to the next field or page. The CR order section should be designed to appear for all patients with qualifying diagnoses, for example heart failure. The recommendation is to make the section mandatory, so that the provider must select something, requiring them to act.
  From a design perspective on the outpatient side, make sure alerts reach community providers who need to see them, and equally, that they do not reach providers that do not need them, as it will just be a nuisance for them. You don’t, for example, want to prompt a dermatologist to refer a patient to CR when the patient comes in to have a mole checked.
  The recommended approach is to target those departments and specialties that make the most sense: internal medicine, family practice, and cardiology, not urology and dermatology.

## Slide 35: WHERE: Referral Location
Ensure ability to automatically refer to all community providers:
Patient convenience is a strong factor in participation.
Ability to refer to multiple programs can increase likelihood of patient participation in CR
Identify all available programs and ensure system is build to refer to them
Notes:   The location of the CR program to which patients are referred will be a key factor in determining the likelihood of their participation and completion of the program. Sometimes patients live far from the referring hospital and have a closer option available to them, or an option with more convenient hours.
  While some hospitals may rely on CC staff to discuss CR program options with patients, may design their AR systems to refer to any CR programs in which their patients might wish to enroll. If this is the case at your hospital, you will need to provide the names of other CR programs available locally or in surrounding communities to your IT staff.
  BE ADVISED: CR champions may need to advocate with leadership on behalf of their patients for the option to make external referrals.

## Slide 36: To Learn More...
See Chapter 3 of the AR Implementation Guide for:
Preparing to Design EMR Specifications
Creating EMR Specifications

## Slide 37: Chapter 4: Testing and Fine-Tuning
Notes:   This chapter outlines considerations for testing and fine-tuning the design of your AR.

## Slide 38: Testing Phases
Define Your Testing Process
Initial Bench Testing
Pilot Testing
Hospital System-Wide Testing
Notes:   There can be several different phases of testing depending on the size of the institution and its experience making system wide changes. However, no matter the size and experience, there should be a plan in place to test the designed AR mechanism before it is implemented.

## Slide 39: Develop Your Testing Plan
What testing phases do you need?
What should each accomplish?
Who should be involved?
What should you be tracking and monitoring?
How will you get feedback from frontline staff?
How will you know when you’re ready for the next phase?
Notes:   You will need to develop a testing plan for each phase of testing that you wish to conduct.
  This slide describes the questions that you and your team will need to answer in developing plans for each phase of testing.

## Slide 40: Bench Testing
Goal: Verify that programming is correctly identifying eligible patients
Process | Use test cases Perform in a secure environment that doesn’t risk patient care Ensure all eligible patients are referred Confirm that no ineligible patients are referred See that referral notifications are going to the correct provider Ensure other requirements are being met
Tips | Providing clear guidance to programmers shortens the process. Proceeding without rigorous bench testing is a common cause of implementation failure.
Notes:   Bench testing is a process used to assess the accuracy, completeness, and quality of the newly programmed EMR in identifying eligible patients for CR. It involves manually executing test cases without using automation tools to find bugs in the system. The goal is to ensure the application is error-free and is working to the specified functional requirements.

## Slide 41: Pilot Testing
Goal: Verify that the AR order set is performing as expected in a small environment.
Process | Select a unit that: Has bought-into the idea of AR Has the ability to select the physicians who will get the AR order Offers the ability to work off hours to minimize risk (evenings/weekends) After using test cases, choose a few live patients to test
Tips | Use the success of Bench Testing to determine your time period for Pilot Testing. Determine how long (days/ weeks/months) you will need to test BEFORE planning for Go-Live.
Notes:   Pilot testing requires selection of an appropriate hospital unit for testing use cases and then some live patients. It’s important to select a unit that has both bought into the idea of an AR order set in the EMR and has the capacity. Pick a unit with patients who have been assigned the relevant ICD-10 codes and relevant providers who’ll need to sign for CR orders to get the volume of orders necessary to test the order set. Find out if you have the ability to work with pre-selected physicians. Don’t forget the evening and night shifts. Run a quick pre-in-service about what to expect and a quick post-in-service with survey to collect feedback. This is your chance to work out any glitches before Go-Live.
  At the conclusion of pilot testing, huddle with your implementation team to debrief about what worked, anything that didn’t work, and the plan and timeline to fix before Go-Live. If there are problems, repeat pilot testing before moving to hospital implementation.
  Once the team is satisfied that the testing success criteria have been met, it’s time to move onto hospital-wide implementation, also known as Go Live.

## Slide 42: To Learn More About Pilot Testing…
See Chapter 4 of the AR Implementation Guide for further guidance about:
Defining Your Testing Process
Bench Testing Steps & Sample Test Cases
Pilot Testing
View the Recording of Building and Implementing a Successful Automatic Referral System
for further discussion of defining the testing process and creating success criteria
Notes: Training Module 5 -- Building and Implementing a Successful Automatic Referral System == explores the important relationship between automatic referral and care coordination and discusses the necessary factors for designing an effective automatic referral system. The training session concludes with steps hospitals need to take to test a new automatic referral system before implementing.
Topics covered in this module include:
Reviewing the important relationship between automatic referral and care coordination.
Exploring the important factors to think through when designing the EMR specifications for automatic referral to cardiac rehabilitation.
Creating a testing plan for the newly designed automatic referral system:
  Defining the testing process
  Creating success criteria
  Allowing for adjustments and refinements
  Preparing for implementation

## Slide 43: Chapter 5: Preparing to “GO LIVE”
Notes:   This chapter covers the preparation needed for activation of the AR.

## Slide 44: Preparing for GO LIVE
“GO LIVE” is the phase in which you roll out use of your new automated referrals system
“GO LIVE” begins when your AR order set works as intended in your EMR
To prepare for going live:
  Determine whose support will be need to ensure a smooth transition
  Conduct planning sessions to discuss roles and responsibilities during this phase
  Develop a plan for educating and generating support from colleagues who will be impacted

## Slide 45: Team Member Roles & Responsibilities
CR Champion serves as the liaison between the team and leadership, owns creation of one-page overview document/elevator speech and communication of it, develops the Go-Live plan, leads the huddles until the AR order set is successfully implemented.
Executive Cardiac and EMR/IT Leadership signals the importance of the initiative, voices support, and has visible involvement.
QI Leader develops the data monitoring and feedback plan, advises on testing plan, and monitors the telephone hotline and email during Go-Live.
Data Analytics Coordinator manages the collection and interpretation of the measure data to support AR and supports analysis of the data to inform testing correction needs and update the data monitoring and feedback plan.
Notes:   During the Go Live phase you will need the continuing support of the team members who have supported you to this point. As shown here, everyone has a critical role.

## Slide 46: Team Member Roles & Responsibilities (con’t)
EMR/IT Staff should be prepared to quickly update the EMR as the AR order set testing presents bugs. They also provide support during the go-live phase.
Cardiac Care Providers and Clinicians should be encouraged to participate in training and provide their feedback about their experiences
CR Clinicians/Staff may be chosen to provide start-up assistance such as helping providers with entering AR orders, ensuring the CR department is receiving the AR orders, and collecting verbal feedback while on the floors helping.

## Slide 47: Support During Go-Live Phase
Provide support for anticipated challenges
  Provide live coverage for hotline phone number for first 24-48 hours
  Monitor email box for questions and provide timely response
  Have staff available to assist new users with entering AR order set
Ensure team representation on all shifts
Hold mid-day huddles until implementation complete
Provide snacks.
Notes:   Preparation, communication, and planned support are the keys to Go-Live success. Even providing snacks and meals is important for minimizing the time personnel need to leave their posts.

## Slide 48: Communications & Education
  Communication Tasks for CR Champion
  Develop a concise, one-page overview of the AR order set.
    Keep the message concise
    Minimize text
    Write in plain language
    Use graphics
  Develop an elevator pitch to regularly and informally educate colleagues.
  Email the overview to all relevant departments and stakeholders
  Ask to speak at unit and department meetings
  Request the overview be posted in staff breakrooms
Notes:   The CR Champion leads the oversight of the communication and education plan and decides what will be done to prepare the hospital for Go-Live. The one-pager the CR Champion develops with input from the team should include everything involved staff need to know in order to complete their part of the AR order set. It should also include your hotline telephone number, email, and names of onsite support staff. Use plain language, minimize text, and use graphics. You will want to illustrate what AR is, how it works, and how to get support. If you have a marketing and/or communication’s department, see if they’ll review your one-pager for effectiveness. A one pager can be used for all communication, for posting, and for emailing. Standardization of the message assures ease of communication as well minimal degradation of the actual education. See Table 4 in the IG for a template.

## Slide 49: Final Prep Step!
  Send hospital-wide reminder e-mails
  1-week before Go-Live
  24 hours before Go-Live

## Slide 50: To Learn More…
See Chapter 5 of the AR Implementation Guide for additional guidance on:
Creating a One-page Document For Go-Live
Communicating and Disseminating the One-page Document
Training Staff Before Go-Live
Additional Staffing and Training Tips

## Slide 51: Chapter 6: Data and Feedback Monitoring
Notes:   Once your AR system is live, you will want to know whether it is having the desired effect. For this reason one final essential task in preparing for launch is putting in place a plan for using data to track your progress!
  For starters, you will want to know whether more eligible patients being enrolled in CR than was the case before you automated your referral system. Answering this question will require that you develop systems for collecting baseline data and then continuing to collect data after your system goes live.
  In order to support continuous improvement of your AR system, you will also want to develop systems for generating feedback from system users about what is and is not working.

## Slide 52: Create a Data & Feedback Monitoring Plan
Key Steps
Determine the availability and transparency of referral-related data.
Decide how often and by whom the data will be reviewed.
Develop a continuous feedback loop and work transformation plan.
Notes:   Creating your data and feedback monitoring plan requires acting on the key steps listed above.

## Slide 53: Key Steps for Using Data to Drive Improvement
Determine the type of data you will need and how you can access it
Examine the data
Supplement quantitative data with user feedback about challenges
Identify reasons for provider opt-outs/work-arounds
Prioritize focus areas for improvement based on the data review and create a plan to address top priorities
Work with IT to make any necessary adjustments.
Notes: You will need to begin by determining what data you can access to ensure you can track key processes for the full completion of the AR order set (from the patient being ordered CR all the way through the patient arriving and completing the first CR appointment).
For suggestions, see Using Cardiac Rehabilitation Referral Performance Measures in a Quality Improvement System.
You may wish to begin by seeing what CR referral data you already have within a clinical data registry can also use AACVPR’s Using Clinical Data Registries to Access Cardiac Rehabilitation Referral Data
See the change concept titled “Use Data to Drive Improvement in Referrals to CR” in the
Million Hearts®/AACVPR Cardiac Rehabilitation Change Package (CRCP) for additional strategies and resources to support your efforts!

## Slide 54: To Learn More About Key Steps…
See Chapter 6 of the AR Implementation Guide for additional guidance on
Determining availability and transparency of referral-related data
Determining who will review the data and how often
Developing a continuous feedback loop and work transformation plan
.

## Slide 55: Chapter 7: Post Launch: Troubleshooting AR
Notes:   . The next slides will help you anticipate challenges and prepare to address them.

## Slide 56: Problem 1
My automatic referral isn’t working the way I expected it to.
QUESTIONS TO CONSIDER AND POTENTIAL SOLUTIONS
Is this a workflow issue? Review your workflow process documents
Is this a technical issue? Check that the AR order set has been correctly programed into your EMR.
If the order set is correct, select a few orders and analyze the process from start
Speak to a clinical end-user and get feedback on the process.
Notes:   Let’s say your AR isn’t working like you thought it would in the EMR.
  Here are some questions to consider:
  Have you accurately captured your workflow processes?
  If you’re confident workflow processes are accurate, has the order set been correctly programed into EMR?
  There are usually multiple ways to build an order set in an EMR so you will need to work with your IT team to determine the best order set type for your hospital providers.
  Here are some issues to check for:
    Are the ICD-10 codes accurate?
    Are pop-ups appearing and leading to pop-up fatigue?
    If using a default order set or discharge smart set, are providers able to work around these orders? Are providers able to skip or opt-out of these orders?
    Note that some systems may use a reflex or cascading order that is suggested by the EMR based on other comparable medical orders (e.g. an EKG was ordered triggering a suggestion of CR).
.

## Slide 57: Problem 2
How do I know if the referrals are increasing or decreasing?
QUESTIONS TO CONSIDER AND POTENTIAL SOLUTIONS
Have you collected baseline data on referrals? Baseline numbers and referral reports should be created before you implement a new AR order set.
Have you developed a data monitoring and feedback plan?
How often are you checking the data/sharing data with stakeholders?
Notes:   In order to know whether automating referrals is having the desired effect, you will need to continue to collect data in accordance with the data and monitoring plan that you developed before you went live. And then you will need to compare the baseline data you collected with referral data collected after going live. Reaching out to your informatics team and asking them to develop tracking reports can be very helpful during this early stage.

## Slide 58: Problem 3
My automatic referral is working, but my referral numbers are not increasing.
QUESTIONS TO CONSIDER AND POTENTIAL SOLUTIONS
Go back to your baseline workflow analysis. Is your new AR design aligned with how providers are using the system?
Do you need to rethink your design and work with your EMR Team to make changes?
Is this design the best option for AR in your organization?
Is there any additional technology available you have not considered?
Have you created AR order set reminders (e.g., newsletters, discussion at rounds, at the elbow reminder cards, etc.)?
Notes:   Let’s say that you’ve determined your AR order set is working, but your referral numbers are not increasing.
  Here are some things you can do:
  Conduct or re-examine your baseline workflow analysis. You want to align the new workflow to match the process that is already in place to help increase adoption.
  Rethink your design based on workflow. Are you utilizing best options available from your EMR?
  Consider whether you need to deploy additional technology.

## Slide 59: To Learn More About Troubleshooting…
  See Chapter 7 of the AR Implementation Guide for additional guidance for
  Preparing for the Go-Live Launch
  Troubleshooting Common Problems
  View the Recording of Troubleshooting Your Automatic Referral System for further discussion of topics covered in the final two sections of this presentation
Notes: In Training Module 7 -- Troubleshooting Your Automatic Referral System -- expert speakers discuss the following topics:
  Developing a data and monitoring plan
  Automatic referral testing.
  Staff training.
  Preparing for roll-out and reinforcement of automatic referral.
  Evaluation and improvement of automatic referral.
  Extending and spreading automatic referral use.